## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a Developer, I want to upload or paste Python code into the web interface so that the system can accept it for analysis. | MUST HAVE | — | Student | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a Developer, I want syntax errors and undefined variables to be detected automatically using AST parsing so that I can fix them quickly. | MUST HAVE | US-01 | Student | 3- Completed
Sprint 2 | Sprint 2 | US-03 | As a Developer, I want my code to be checked against PEP8 style standards so that I can improve coding readability and consistency. | MUST HAVE | US-02 | Student | 3- Completed
Sprint 2 | Sprint 2 | US-04 | As a Developer, I want unused variables and imported modules to be detected automatically so that I can keep my code clean. | MUST HAVE | US-02 | Student | 3- Completed
Sprint 3 | Sprint 3 | US-05 | As a Developer, I want the AI model (LLaMA 3.1 via Groq) to analyse my code and provide intelligent suggestions for improvement. | MUST HAVE | US-03, US-04 | Student | 3- Completed
Sprint 3 | Sprint 3 | US-06 | As a Developer, I want to see before-and-after corrected code snippets so that I can understand exactly what changes were suggested. | SHOULD HAVE | US-05 | Student | 3- Completed
Sprint 4 | Sprint 4 | US-07 | As a Developer, I want the application to be built using the Reflex framework so that both frontend and backend are written in Python. | SHOULD HAVE | US-05 | Student | 3- Completed
Sprint 4 | Sprint 4 | US-08 | As a Developer, I want the web interface to display results in categorised sections (Syntax, Static, AI Analysis) so that the feedback is easy to read. | SHOULD HAVE | US-07 | Student | 3- Completed
Sprint 4 | Sprint 4 | US-09 | As a Developer, I want the system to show a performance score and code metrics (lines, functions, complexity) so that I can measure code quality. | COULD HAVE | US-08 | Student | 2- In Progress
Sprint 4 | Sprint 4 | US-10 | As a Developer, I want the tool to support code upload via file (.py) in addition to paste so that submission is more flexible. | COULD HAVE | US-01 | Student | 1- To Do

## Sheet1
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Est. Hours | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
SPRINT 1 BACKLOG
US-01 | T-01 | Analyze project requirements and define system modules | 04-Dec-25 | 05-Dec-25 | Student | Design | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Set up project folder structure and virtual environment | 2026-02-02 | 2026-02-02 | Student | Setup | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-03 | Implement code input interface (paste text area) | 2026-02-04 | 2026-02-04 | Student | Build | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-04 | Implement syntax validation using Python AST module | 2026-02-05 | 2026-02-05 | Student | Build | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-05 | Test AST parser with valid and invalid Python snippets | 2026-02-06 | 2026-02-12 | Student | Test | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-03 | T-06 | Integrate PEP8 style checker using pycodestyle library | 2026-02-16 | 2026-02-16 | Student | Build | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-07 | Display PEP8 violations with line numbers in UI | 2026-02-18 | 2025-02-18 | Student | Build | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-08 | Build static analyser to detect unused variables using AST | 2026-02-23 | 2026-02-23 | Student | Build | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-09 | Detect unused import statements via AST node visitor | 2026-02-24 | 2026-02-24 | Student | Build | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-10 | Unit test static analyser with sample buggy code | 2026-02-26 | 2026-02-26 | Student | Test | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-05 | T-11 | Integrate LangChain + Groq API for LLaMA 3.1 model | 2026-03-03 | 2026-03-03 | Student | Build | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-12 | Design AI prompt template for code review and suggestions | 2026-03-08 | 2026-03-08 | Student | Design | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-13 | Pass static errors and code to AI and capture response | 2026-03-10 | 2026-03-10 | Student | Build | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-14 | Parse AI response and extract corrected code block | 2026-03-11 | 2026-03-11 | Student | Build | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-15 | Display original vs corrected code side-by-side in UI | 2026-03-11 | 2026-03-13 | Student | Build | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-07 | T-16 | Scaffold Reflex application and configure rxconfig.py | 2026-03-16 | 2026-03-17 | Student | Setup | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-17 | Wire all backend modules to Reflex State class | 2025-03-17 | 2026-03-17 | Student | Build | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-18 | Build responsive UI with result cards for each analysis step | 2026-03-18 | 2026-03-18 | Student | Build | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-19 | Add loading spinner and async state updates | 2026-03-20 | 2026-03-20 | Student | Build | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | None | Analyzed project requirements and designed the system architecture with five modules: Parser, Detector, Suggester, Style Checker, and Web App.
Sprint 1 | Day 2 | Difficulty understanding AST node traversal and visiting different node types for Python code | Reviewed official Python AST documentation, studied NodeVisitor class pattern, and tested sample parsing on small code snippets.
Sprint 1 | Day 3 | Handling unused imports vs. used imports causing false positives | Improved the ErrorVisitor by tracking defined and used name sets separately; added a whitelist for common builtins.
Sprint 1 | Day 4 | PEP8 integration returning too many minor warnings cluttering the output | Filtered PEP8 results to show only critical violations (E1xx, E2xx, W6xx) and grouped by line number.
Sprint 1 | Day 5 | Difficulty selecting a suitable LLM for code analysis due to rate limits on OpenAI API | Identified Groq API with LLaMA 3.1-8b-instant as the model; low latency and free tier sufficient for development.
Sprint 2 | Day 1 | None | Started Sprint 2; began PEP8 checker integration and static variable analysis module.
Sprint 2 | Day 2 | Unused variable detection triggering on loop counters and intentional placeholders | Added underscore-prefix exclusion rule (_var) and loop variable exception logic in the detector.
Sprint 2 | Day 3 | LangChain prompt sometimes returning too long a response causing UI overflow | Added max_tokens parameter and structured the prompt to return sections with clear delimiters.
Sprint 2 | Day 4 | None | Completed static analyser module; wrote test cases for five code scenarios.
Sprint 2 | Day 5 | None | Sprint 2 review and retrospective completed; all tasks marked done.
Sprint 3 | Day 1 | None | Started Sprint 3; integrated Groq API key and confirmed LLaMA 3.1 model responds correctly.
Sprint 3 | Day 2 | AI response containing markdown code blocks not rendering properly in Reflex | Used rx.markdown() component to render AI output and applied custom CSS for code blocks.
Sprint 3 | Day 3 | Before/after code display layout causing horizontal scroll on mobile | Switched from side-by-side to stacked layout for screens under 768px using Reflex conditional rendering.
Sprint 3 | Day 4 | None | Completed AI analysis module and before/after code display; tested with five different buggy Python scripts.
Sprint 3 | Day 5 | None | Sprint 3 review completed; demo shown to instructor; minor UI refinements noted for Sprint 4.
Sprint 4 | Day 1 | None | Started Sprint 4; scaffolded full Reflex application and wired all backend modules into State class.
Sprint 4 | Day 2 | Async generator (yield) in Reflex state not reflecting intermediate UI updates | Used multiple yield statements between each step (Syntax → Static → AI) to stream results progressively.
Sprint 4 | Day 3 | Code metrics calculation (cyclomatic complexity) requiring additional AST traversal logic | Implemented function-level complexity counter using AST; tracked If, For, While, Try, With node counts.
Sprint 4 | Day 4 | None | UI polished; result cards formatted with step labels, colour-coded badges for error types.
Sprint 4 | Day 5 | None | Final integration testing completed; application running on localhost:3000 with all five modules functional.

## Retrospection
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | 1 | 2026-02-02 | 2026-02-13 | Student | Write unit tests alongside each module from day one | Delaying documentation to the last day of the sprint | Daily stand-up notes and impediment logging | Created a unit test file per module starting Sprint 2
2 | 2 | 2026-02-16 | 2026-02-28 | Student | Peer-review code before marking tasks as complete | Hardcoding test inputs; use parametrised test cases instead | Filtering and grouping analysis output before display | Added code review checklist to sprint board
3 | 3 | 2026-03-03 | 2026-03-13 | Student | Add loading/progress indicators for each async step | Over-engineering prompt templates; keep them concise | Using structured prompts with clear section delimiters | Implemented step-by-step yield in Reflex state handler
4 | 4 | 2025-03-16 | 2026-03-28 | Student | Plan UI layout on paper before coding Reflex components | Ignoring mobile responsiveness until end of sprint | Modular backend design (parser/detector/suggester separated) | Completed responsive layout; all modules integrated and tested